## 1 Iteration
OrganizationManagement |  | FIRST ITERATION | WILL DO: First steps of playing a competition, only use cases related to lift weight change, lift status, lifters weighin data are to be done
CompetitionManagementdrawLifters |  |  | WONT DO: timers, lifter categories use cases
BatchManagementassignLifterToBatch
TimerManagementstart
SpectatorManagementshowCompetitions
T
USE CASE NAME | Risk 1 Team experience with visual apps | Risk 2 Complexity | Risk 2 Business Needs | Risk 3 Team Needs | Total | Use Cases to be done
initPlay | 10 | 10 | 10 | 10 | 100% | X
editLiftWeightChange | 10 | 9 | 10 | 10 | 97.5% | X
editLiftStatus | 10 | 9 | 10 | 10 | 97.5% | X
editLiftValue | 10 | 9 | 10 | 10 | 97.5% | X
introduceWeighinData | 10 | 6 | 10 | 10 | 90% | X
finishPlay | 10 | 8 | 10 | 7 | 87.5%
showCategories | 10 | 6 | 10 | 9 | 87.5%
showLifterCategory | 10 | 7 | 10 | 7 | 85%
editBodyWeightCategory | 10 | 6 | 8 | 9 | 82.5%
createClassifications | 10 | 9 | 8 | 3 | 75%
deleteBodyWeightCategory | 10 | 6 | 3 | 9 | 70%
createAct | 10 | 8 | 6 | 4 | 70%
showClassifications | 10 | 6 | 8 | 3 | 67.5%
downloadClassifications | 10 | 9 | 1 | 3 | 57.5%
showResults | 10 | 8 | 1 | 3 | 55%
showCompetitions | 10 | 6 | 1 | 3 | 50%
showInscribedLifters | 10 | 6 | 1 | 3 | 50%
downloadAct | 10 | 8 | 1 | 1 | 50%
pause | 10 | 2 | 1 | 7 | 50%
resume | 10 | 2 | 1 | 7 | 50%
setDuration | 10 | 2 | 1 | 7 | 50%
stop | 10 | 2 | 1 | 7 | 50%
showCompetition | 10 | 6 | 1 | 3 | 50%
showBatchInscriptions | 10 | 6 | 1 | 3 | 50%
showBatchWeighins | 10 | 6 | 1 | 3 | 50%
showFinishedBatches | 10 | 6 | 1 | 3 | 50%
showLiveBatchInPlay | 10 | 6 | 1 | 3 | 50%
downloadResults | 10 | 8 | 1 | 1 | 50%
showClubs | 10 | 6 | 1 | 1 | 45%
showOrganizers | 10 | 6 | 1 | 1 | 45%
showInscribers | 10 | 6 | 1 | 1 | 45%
showInscriptions | 10 | 6 | 1 | 1 | 45%
inscribeLifter | 10 | 6 | 1 | 1 | 45%
uninscribeLifter | 10 | 6 | 1 | 1 | 45%
unassignLifterToBatch | 10 | 6 | 1 | 1 | 45%
assignLifterToBatch | 10 | 6 | 1 | 1 | 45%
showBatches | 10 | 6 | 1 | 1 | 45%
editBatch | 10 | 6 | 1 | 1 | 45%
login | 10 | 4 | 1 | 1 | 40%
logout | 10 | 4 | 1 | 1 | 40%
editClubs | 10 | 3 | 1 | 1 | 37.5%
deleteClubs | 10 | 3 | 1 | 1 | 37.5%
editOrganizer | 10 | 3 | 1 | 1 | 37.5%
deleteOrganizer | 10 | 3 | 1 | 1 | 37.5%
editInscriber | 10 | 3 | 1 | 1 | 37.5%
deleteInscriber | 10 | 3 | 1 | 1 | 37.5%
deleteCompetition | 10 | 3 | 1 | 1 | 37.5%
editCompetition | 10 | 3 | 1 | 1 | 37.5%
deleteBatch | 10 | 3 | 1 | 1 | 37.5%
openInscriptionsPeriod | 10 | 2 | 1 | 1 | 35%
closeInscriptions | 10 | 2 | 1 | 1 | 35%
launch | 10 | 2 | 1 | 1 | 35%

## 2 Iteration
OrganizationManagement |  | SECOND ITERATION | WILL DO : Lifter category is included in play competition
CompetitionManagementdrawLifters |  |  | WILL DO: Categories management is to be done
BatchManagementassignLifterToBatch |  |  | WONT DO: Timer (in play)
TimerManagementstart
SpectatorManagementshowCompetitions
T
USE CASE NAME | Risk 1 Team experience with visual apps | Risk 2 Complexity | Risk 2 Business Needs | Risk 3 Team Needs | Total | Use Cases to be done
showLifterCategory | 10 | 7 | 10 | 10 | 92.5% | x
showCategories | 10 | 6 | 10 | 10 | 90% | x
editBodyWeightCategory | 10 | 6 | 8 | 10 | 85% | x
deleteBodyWeightCategory | 10 | 6 | 8 | 10 | 85% | x
finishPlay | 10 | 8 | 10 | 3 | 77.5%
createClassifications | 10 | 9 | 8 | 3 | 75%
createAct | 10 | 8 | 6 | 4 | 70%
showClassifications | 10 | 6 | 8 | 3 | 67.5%
downloadClassifications | 10 | 9 | 1 | 3 | 57.5%
showResults | 10 | 8 | 1 | 3 | 55%
showCompetitions | 10 | 6 | 1 | 3 | 50%
showInscribedLifters | 10 | 6 | 1 | 3 | 50%
downloadAct | 10 | 8 | 1 | 1 | 50%
pause | 10 | 2 | 1 | 7 | 50%
resume | 10 | 2 | 1 | 7 | 50%
setDuration | 10 | 2 | 1 | 7 | 50%
stop | 10 | 2 | 1 | 7 | 50%
showCompetition | 10 | 6 | 1 | 3 | 50%
showBatchInscriptions | 10 | 6 | 1 | 3 | 50%
showBatchWeighins | 10 | 6 | 1 | 3 | 50%
showFinishedBatches | 10 | 6 | 1 | 3 | 50%
showLiveBatchInPlay | 10 | 6 | 1 | 3 | 50%
downloadResults | 10 | 8 | 1 | 1 | 50%
showClubs | 10 | 6 | 1 | 1 | 45%
showOrganizers | 10 | 6 | 1 | 1 | 45%
showInscribers | 10 | 6 | 1 | 1 | 45%
showInscriptions | 10 | 6 | 1 | 1 | 45%
inscribeLifter | 10 | 6 | 1 | 1 | 45%
uninscribeLifter | 10 | 6 | 1 | 1 | 45%
unassignLifterToBatch | 10 | 6 | 1 | 1 | 45%
assignLifterToBatch | 10 | 6 | 1 | 1 | 45%
showBatches | 10 | 6 | 1 | 1 | 45%
editBatch | 10 | 6 | 1 | 1 | 45%
login | 10 | 4 | 1 | 1 | 40%
logout | 10 | 4 | 1 | 1 | 40%
editClubs | 10 | 3 | 1 | 1 | 37.5%
deleteClubs | 10 | 3 | 1 | 1 | 37.5%
editOrganizer | 10 | 3 | 1 | 1 | 37.5%
deleteOrganizer | 10 | 3 | 1 | 1 | 37.5%
editInscriber | 10 | 3 | 1 | 1 | 37.5%
deleteInscriber | 10 | 3 | 1 | 1 | 37.5%
deleteCompetition | 10 | 3 | 1 | 1 | 37.5%
editCompetition | 10 | 3 | 1 | 1 | 37.5%
deleteBatch | 10 | 3 | 1 | 1 | 37.5%
openInscriptionsPeriod | 10 | 2 | 1 | 1 | 35%
closeInscriptions | 10 | 2 | 1 | 1 | 35%
launch | 10 | 2 | 1 | 1 | 35%
FINISHED USE CASES
initPlay
editLiftWeightChange
editLiftStatus
editLiftValue
introduceWeighinData

## 3 Iteration
OrganizationManagement |  | THIRD ITERATION | WILL DO: complete timer use cases
CompetitionManagementdrawLifters
BatchManagementassignLifterToBatch
TimerManagementstart
SpectatorManagementshowCompetitions
T
USE CASE NAME | Risk 1 Team experience with visual apps | Risk 2 Complexity | Risk 2 Business Needs | Risk 3 Team Needs | Total | Use Cases to be done
pause | 10 | 2 | 1 | 10 | 57.5% | x
resume | 10 | 2 | 1 | 10 | 57.5% | x
setDuration | 10 | 2 | 1 | 10 | 57.5% | x
stop | 10 | 2 | 1 | 10 | 57.5% | x
createClassifications | 10 | 9 | 2 | 1 | 55%
showResults | 10 | 8 | 1 | 3 | 55%
downloadClassifications | 10 | 9 | 1 | 1 | 52.5%
createAct | 10 | 8 | 2 | 1 | 52.5%
finishPlay | 10 | 8 | 2 | 1 | 52.5%
showCompetitions | 10 | 6 | 1 | 3 | 50%
showInscribedLifters | 10 | 6 | 1 | 3 | 50%
downloadAct | 10 | 8 | 1 | 1 | 50%
showCompetition | 10 | 6 | 1 | 3 | 50%
showBatchInscriptions | 10 | 6 | 1 | 3 | 50%
showBatchWeighins | 10 | 6 | 1 | 3 | 50%
showFinishedBatches | 10 | 6 | 1 | 3 | 50%
showLiveBatchInPlay | 10 | 6 | 1 | 3 | 50%
downloadResults | 10 | 8 | 1 | 1 | 50%
showClassifications | 10 | 6 | 2 | 1 | 47.5%
showClubs | 10 | 6 | 1 | 1 | 45%
showOrganizers | 10 | 6 | 1 | 1 | 45%
showInscribers | 10 | 6 | 1 | 1 | 45%
showInscriptions | 10 | 6 | 1 | 1 | 45%
inscribeLifter | 10 | 6 | 1 | 1 | 45%
uninscribeLifter | 10 | 6 | 1 | 1 | 45%
unassignLifterToBatch | 10 | 6 | 1 | 1 | 45%
assignLifterToBatch | 10 | 6 | 1 | 1 | 45%
showBatches | 10 | 6 | 1 | 1 | 45%
editBatch | 10 | 6 | 1 | 1 | 45%
login | 10 | 4 | 1 | 1 | 40%
logout | 10 | 4 | 1 | 1 | 40%
editClubs | 10 | 3 | 1 | 1 | 37.5%
deleteClubs | 10 | 3 | 1 | 1 | 37.5%
editOrganizer | 10 | 3 | 1 | 1 | 37.5%
deleteOrganizer | 10 | 3 | 1 | 1 | 37.5%
editInscriber | 10 | 3 | 1 | 1 | 37.5%
deleteInscriber | 10 | 3 | 1 | 1 | 37.5%
deleteCompetition | 10 | 3 | 1 | 1 | 37.5%
editCompetition | 10 | 3 | 1 | 1 | 37.5%
deleteBatch | 10 | 3 | 1 | 1 | 37.5%
openInscriptionsPeriod | 10 | 2 | 1 | 1 | 35%
closeInscriptions | 10 | 2 | 1 | 1 | 35%
launch | 10 | 2 | 1 | 1 | 35%
FINISHED USE CASES
initPlay
editLiftWeightChange
editLiftStatus
editLiftValue
introduceWeighinData
showLifterCategory
showCategories
editBodyWeightCategory
deleteBodyWeightCategory

## 4 Iteration
OrganizationManagement |  | THIRD ITERATION | WILL DO: complete competition play with creation/download acts and finish play
CompetitionManagementdrawLifters |  |  | WILL DO: login/logout
BatchManagementassignLifterToBatch
TimerManagementstart
SpectatorManagementshowCompetitions
T
USE CASE NAME | Risk 1 Team experience with visual apps | Risk 2 Complexity | Risk 2 Business Needs | Risk 3 Team Needs | Total | Use Cases to be done
createAct | 10 | 8 | 2 | 10 | 75% | x
finishPlay | 10 | 8 | 2 | 10 | 75% | x
downloadAct | 10 | 8 | 1 | 10 | 72.5% | x
login | 10 | 4 | 1 | 10 | 62.5% | x
logout | 10 | 4 | 1 | 10 | 62.5% | x
createClassifications | 10 | 9 | 2 | 1 | 55%
showResults | 10 | 8 | 1 | 3 | 55%
downloadClassifications | 10 | 9 | 1 | 1 | 52.5%
showCompetitions | 10 | 6 | 1 | 3 | 50%
showInscribedLifters | 10 | 6 | 1 | 3 | 50%
showCompetition | 10 | 6 | 1 | 3 | 50%
showBatchInscriptions | 10 | 6 | 1 | 3 | 50%
showBatchWeighins | 10 | 6 | 1 | 3 | 50%
showFinishedBatches | 10 | 6 | 1 | 3 | 50%
showLiveBatchInPlay | 10 | 6 | 1 | 3 | 50%
downloadResults | 10 | 8 | 1 | 1 | 50%
showClassifications | 10 | 6 | 2 | 1 | 47.5%
showClubs | 10 | 6 | 1 | 1 | 45%
showOrganizers | 10 | 6 | 1 | 1 | 45%
showInscribers | 10 | 6 | 1 | 1 | 45%
showInscriptions | 10 | 6 | 1 | 1 | 45%
inscribeLifter | 10 | 6 | 1 | 1 | 45%
uninscribeLifter | 10 | 6 | 1 | 1 | 45%
unassignLifterToBatch | 10 | 6 | 1 | 1 | 45%
assignLifterToBatch | 10 | 6 | 1 | 1 | 45%
showBatches | 10 | 6 | 1 | 1 | 45%
editBatch | 10 | 6 | 1 | 1 | 45%
editClubs | 10 | 3 | 1 | 1 | 37.5%
deleteClubs | 10 | 3 | 1 | 1 | 37.5%
editOrganizer | 10 | 3 | 1 | 1 | 37.5%
deleteOrganizer | 10 | 3 | 1 | 1 | 37.5%
editInscriber | 10 | 3 | 1 | 1 | 37.5%
deleteInscriber | 10 | 3 | 1 | 1 | 37.5%
deleteCompetition | 10 | 3 | 1 | 1 | 37.5%
editCompetition | 10 | 3 | 1 | 1 | 37.5%
deleteBatch | 10 | 3 | 1 | 1 | 37.5%
openInscriptionsPeriod | 10 | 2 | 1 | 1 | 35%
closeInscriptions | 10 | 2 | 1 | 1 | 35%
launch | 10 | 2 | 1 | 1 | 35%
FINISHED USE CASES
initPlay
editLiftWeightChange
editLiftStatus
editLiftValue
introduceWeighinData
showLifterCategory
showCategories
editBodyWeightCategory
deleteBodyWeightCategory
pause
resume
setDuration
stop

## 5 Iteration
OrganizationManagement |  | THIRD ITERATION | WILL DO: clubs, organizers, inscribers management
CompetitionManagementdrawLifters
BatchManagementassignLifterToBatch
TimerManagementstart
SpectatorManagementshowCompetitions
T
USE CASE NAME | Risk 1 Team experience with visual apps | Risk 2 Complexity | Risk 2 Business Needs | Risk 3 Team Needs | Total | Use Cases to be done
showClubs | 10 | 6 | 6 | 8 | 75% | x
showOrganizers | 10 | 6 | 6 | 8 | 75% | x
showInscribers | 10 | 6 | 6 | 8 | 75% | x
editClubs | 10 | 3 | 6 | 8 | 67.5% | x
deleteClubs | 10 | 3 | 6 | 8 | 67.5% | x
editOrganizer | 10 | 3 | 6 | 8 | 67.5% | x
deleteOrganizer | 10 | 3 | 6 | 8 | 67.5% | x
editInscriber | 10 | 3 | 6 | 8 | 67.5% | x
deleteInscriber | 10 | 3 | 4 | 8 | 62.5% | x
createClassifications | 10 | 9 | 2 | 3 | 60%
showResults | 10 | 8 | 1 | 3 | 55%
downloadClassifications | 10 | 9 | 1 | 1 | 52.5%
showCompetitions | 10 | 6 | 1 | 3 | 50%
showInscribedLifters | 10 | 6 | 1 | 3 | 50%
showCompetition | 10 | 6 | 1 | 3 | 50%
showBatchInscriptions | 10 | 6 | 1 | 3 | 50%
showBatchWeighins | 10 | 6 | 1 | 3 | 50%
showFinishedBatches | 10 | 6 | 1 | 3 | 50%
showLiveBatchInPlay | 10 | 6 | 1 | 3 | 50%
downloadResults | 10 | 8 | 1 | 1 | 50%
showClassifications | 10 | 6 | 2 | 1 | 47.5%
showInscriptions | 10 | 6 | 1 | 1 | 45%
inscribeLifter | 10 | 6 | 1 | 1 | 45%
uninscribeLifter | 10 | 6 | 1 | 1 | 45%
unassignLifterToBatch | 10 | 6 | 1 | 1 | 45%
assignLifterToBatch | 10 | 6 | 1 | 1 | 45%
showBatches | 10 | 6 | 1 | 1 | 45%
editBatch | 10 | 6 | 1 | 1 | 45%
deleteCompetition | 10 | 3 | 1 | 1 | 37.5%
editCompetition | 10 | 3 | 1 | 1 | 37.5%
deleteBatch | 10 | 3 | 1 | 1 | 37.5%
openInscriptionsPeriod | 10 | 2 | 1 | 1 | 35%
closeInscriptions | 10 | 2 | 1 | 1 | 35%
launch | 10 | 2 | 1 | 1 | 35%
FINISHED USE CASES
initPlay
editLiftWeightChange
editLiftStatus
editLiftValue
introduceWeighinData
showLifterCategory
showCategories
editBodyWeightCategory
deleteBodyWeightCategory
pause
resume
setDuration
stop
createAct
finishPlay
downloadAct
login
logout

## 6 Iteration
OrganizationManagement |  | THIRD ITERATION | WILL DO: competition, batches management
CompetitionManagementdrawLifters
BatchManagementassignLifterToBatch
TimerManagementstart
SpectatorManagementshowCompetitions
T
USE CASE NAME | Risk 1 Team experience with visual apps | Risk 2 Complexity | Risk 2 Business Needs | Risk 3 Team Needs | Total | Use Cases to be done
editBatch | 10 | 6 | 9 | 9 | 85% | x
deleteBatch | 10 | 6 | 9 | 9 | 85% | x
showBatches | 10 | 6 | 9 | 8 | 82.5% | x
editCompetition | 10 | 3 | 10 | 10 | 82.5% | x
showCompetition | 10 | 6 | 7 | 7 | 75% | x
deleteCompetition | 10 | 3 | 8 | 8 | 72.5% | x
showCompetitions | 10 | 6 | 1 | 9 | 65% | x
createClassifications | 10 | 9 | 2 | 3 | 60%
showResults | 10 | 8 | 1 | 3 | 55%
downloadClassifications | 10 | 9 | 1 | 1 | 52.5%
showInscribedLifters | 10 | 6 | 1 | 3 | 50%
showBatchInscriptions | 10 | 6 | 1 | 3 | 50%
showBatchWeighins | 10 | 6 | 1 | 3 | 50%
showFinishedBatches | 10 | 6 | 1 | 3 | 50%
showLiveBatchInPlay | 10 | 6 | 1 | 3 | 50%
downloadResults | 10 | 8 | 1 | 1 | 50%
showClassifications | 10 | 6 | 2 | 1 | 47.5%
showInscriptions | 10 | 6 | 1 | 1 | 45%
inscribeLifter | 10 | 6 | 1 | 1 | 45%
uninscribeLifter | 10 | 6 | 1 | 1 | 45%
unassignLifterToBatch | 10 | 6 | 1 | 1 | 45%
assignLifterToBatch | 10 | 6 | 1 | 1 | 45%
openInscriptionsPeriod | 10 | 2 | 1 | 1 | 35%
closeInscriptions | 10 | 2 | 1 | 1 | 35%
launch | 10 | 2 | 1 | 1 | 35%
FINISHED USE CASES
initPlay
editLiftWeightChange
editLiftStatus
editLiftValue
introduceWeighinData
showLifterCategory
showCategories
editBodyWeightCategory
deleteBodyWeightCategory
pause
resume
setDuration
stop
createAct
finishPlay
downloadAct
login
logout
showClubs
showOrganizers
showInscribers
editClubs
deleteClubs
editOrganizer
deleteOrganizer
editInscriber
deleteInscriber

## 7 Iteration
OrganizationManagement |  | THIRD ITERATION | WILL DO: inscribe lifters, manage lifters with/to batch
CompetitionManagementdrawLifters
BatchManagementassignLifterToBatch
TimerManagementstart
SpectatorManagementshowCompetitions
T
USE CASE NAME | Risk 1 Team experience with visual apps | Risk 2 Complexity | Risk 2 Business Needs | Risk 3 Team Needs | Total | Use Cases to be done
unassignLifterToBatch | 10 | 6 | 10 | 10 | 90% | x
assignLifterToBatch | 10 | 6 | 10 | 10 | 90% | x
inscribeLifter | 10 | 6 | 9 | 9 | 85% | x
uninscribeLifter | 10 | 6 | 9 | 9 | 85% | x
showInscriptions | 10 | 6 | 8 | 9 | 82.5% | x
showInscribedLifters | 10 | 6 | 8 | 8 | 80% | x
createClassifications | 10 | 9 | 2 | 3 | 60%
showResults | 10 | 8 | 1 | 3 | 55%
downloadClassifications | 10 | 9 | 1 | 1 | 52.5%
showBatchInscriptions | 10 | 6 | 1 | 3 | 50%
showBatchWeighins | 10 | 6 | 1 | 3 | 50%
showFinishedBatches | 10 | 6 | 1 | 3 | 50%
showLiveBatchInPlay | 10 | 6 | 1 | 3 | 50%
downloadResults | 10 | 8 | 1 | 1 | 50%
showClassifications | 10 | 6 | 2 | 1 | 47.5%
openInscriptionsPeriod | 10 | 2 | 1 | 1 | 35%
closeInscriptions | 10 | 2 | 1 | 1 | 35%
launch | 10 | 2 | 1 | 1 | 35%
FINISHED USE CASES
initPlay
editLiftWeightChange
editLiftStatus
editLiftValue
introduceWeighinData
showLifterCategory
showCategories
editBodyWeightCategory
deleteBodyWeightCategory
pause
resume
setDuration
stop
createAct
finishPlay
downloadAct
login
logout
showClubs
showOrganizers
showInscribers
editClubs
deleteClubs
editOrganizer
deleteOrganizer
editInscriber
deleteInscriber
editBatch
deleteBatch
showBatches
editCompetition
showCompetition
deleteCompetition
showCompetitions

## 8 Iteration
OrganizationManagement |  | THIRD ITERATION | WILL DO: manage inscription periods, classification management
CompetitionManagementdrawLifters
BatchManagementassignLifterToBatch
TimerManagementstart
SpectatorManagementshowCompetitions
T
USE CASE NAME | Risk 1 Team experience with visual apps | Risk 2 Complexity | Risk 2 Business Needs | Risk 3 Team Needs | Total | Use Cases to be done
downloadClassifications | 10 | 9 | 9 | 9 | 92.5% | x
showClassifications | 10 | 6 | 9 | 8 | 82.5% | x
openInscriptionsPeriod | 10 | 2 | 10 | 10 | 80% | x
closeInscriptions | 10 | 2 | 10 | 10 | 80% | x
createClassifications | 10 | 9 | 2 | 3 | 60% | x
showResults | 10 | 8 | 1 | 3 | 55%
showBatchInscriptions | 10 | 6 | 1 | 3 | 50%
showBatchWeighins | 10 | 6 | 1 | 3 | 50%
showFinishedBatches | 10 | 6 | 1 | 3 | 50%
showLiveBatchInPlay | 10 | 6 | 1 | 3 | 50%
downloadResults | 10 | 8 | 1 | 1 | 50%
launch | 10 | 2 | 1 | 1 | 35%
FINISHED USE CASES
initPlay
editLiftWeightChange
editLiftStatus
editLiftValue
introduceWeighinData
showLifterCategory
showCategories
editBodyWeightCategory
deleteBodyWeightCategory
pause
resume
setDuration
stop
createAct
finishPlay
downloadAct
login
logout
showClubs
showOrganizers
showInscribers
editClubs
deleteClubs
editOrganizer
deleteOrganizer
editInscriber
deleteInscriber
editBatch
deleteBatch
showBatches
editCompetition
showCompetition
deleteCompetition
showCompetitions
unassignLifterToBatch
assignLifterToBatch
inscribeLifter
uninscribeLifter
showInscriptions
showInscribedLifters

## 9 Iteration
OrganizationManagement |  | THIRD ITERATION | WILL DO: show batches in play, batches results and allow download
CompetitionManagementdrawLifters
BatchManagementassignLifterToBatch
TimerManagementstart
SpectatorManagementshowCompetitions
T
USE CASE NAME | Risk 1 Team experience with visual apps | Risk 2 Complexity | Risk 2 Business Needs | Risk 3 Team Needs | Total | Use Cases to be done
showLiveBatchInPlay | 10 | 6 | 9 | 9 | 85% | x
launch | 10 | 2 | 10 | 10 | 80%
showResults | 10 | 8 | 9 | 3 | 75% | x
showBatchInscriptions | 10 | 6 | 9 | 3 | 70%
showBatchWeighins | 10 | 6 | 9 | 3 | 70%
showFinishedBatches | 10 | 6 | 9 | 3 | 70% | x
downloadResults | 10 | 8 | 9 | 1 | 70% | x
FINISHED USE CASES
initPlay
editLiftWeightChange
editLiftStatus
editLiftValue
introduceWeighinData
showLifterCategory
showCategories
editBodyWeightCategory
deleteBodyWeightCategory
pause
resume
setDuration
stop
createAct
finishPlay
downloadAct
login
logout
showClubs
showOrganizers
showInscribers
editClubs
deleteClubs
editOrganizer
deleteOrganizer
editInscriber
deleteInscriber
editBatch
deleteBatch
showBatches
editCompetition
showCompetition
deleteCompetition
showCompetitions
unassignLifterToBatch
assignLifterToBatch
inscribeLifter
uninscribeLifter
showInscriptions
showInscribedLifters
downloadClassifications
showClassifications
openInscriptionsPeriod
closeInscriptions
createClassifications

## 10 Iteration
OrganizationManagement |  | THIRD ITERATION | WILL DO: show batches in play, batches results and allow download
CompetitionManagementdrawLifters
BatchManagementassignLifterToBatch
TimerManagementstart
SpectatorManagementshowCompetitions
T
USE CASE NAME | Risk 1 Team experience with visual apps | Risk 2 Complexity | Risk 2 Business Needs | Risk 3 Team Needs | Total | Use Cases to be done
launch | 10 | 2 | 10 | 8 | 75% | x
showBatchInscriptions | 10 | 6 | 9 | 10 | 87.5% | x
showBatchWeighins | 10 | 6 | 9 | 9 | 85% | x
FINISHED USE CASES
initPlay
editLiftWeightChange
editLiftStatus
editLiftValue
introduceWeighinData
showLifterCategory
showCategories
editBodyWeightCategory
deleteBodyWeightCategory
pause
resume
setDuration
stop
createAct
finishPlay
downloadAct
login
logout
showClubs
showOrganizers
showInscribers
editClubs
deleteClubs
editOrganizer
deleteOrganizer
editInscriber
deleteInscriber
editBatch
deleteBatch
showBatches
editCompetition
showCompetition
deleteCompetition
showCompetitions
unassignLifterToBatch
assignLifterToBatch
inscribeLifter
uninscribeLifter
showInscriptions
showInscribedLifters
downloadClassifications
showClassifications
openInscriptionsPeriod
closeInscriptions
createClassifications
showLiveBatchInPlay
showResults
showFinishedBatches
downloadResults